## Planning req for WS (hidden)
Task ID | Task | Task Desc
1 | Sustainable VLAN Scalability | We trunk ~2000 VLANs towards each UCS FI port-channel however with DELL we have to trunk it to all server port-channels or ac-tive/standby links. Each Cisco ACI leaf switch has a certain VLAN scalability (Cisco states 64000). In theory that means a completely unoccupied switch could be used to support only 32 with 2000 VLANs on it (32x2000 = 64000). If this is right (to be confirmed by Cisco) then our existing network infrastructure may not be able to handle the new servers in test and we would also need to validate potential increase in HW investments for Prod. To be Discussed in meeting with Dell Subject Matter Expert. | lldp between Servers and Network
2 | VMM domain configuration on APIC | We use Cisco ACI with VMware VDS Integration where APIC deploys port groups into vCenter. This is achieved by creating Read-Write VMM Domain. The configuration is set with certain policies for config-uring port-channel towards UCS Fis and mac-pinning for vDS itself. We need to ascertain whether we can use the existing domain or whether we have to create a new one for DELL servers (which means new datacenter in vCenter) and for that there are some caveats to en-sure connectivity between the new and existing compute setup to per-form virtual machines vMotion. To be Discussed in meeting with Dell Subject Matter Expert. | new VMM Domain to configure but not necressary to be discussed with Dell
3 | PowerFlex Compute Nodes installed with ESXi Server | what is the Process behind? What can be automatet, what needs to be changed/Add
4 | VLAN for Management | can we use the existing VLANS for Management (1331, 1332,329) also for the new EXSi Servers | Better having new VLAN´s
5 | Networks for in-guest-Storage | Storage Interfaces from VM´s needs to connect to the new Storage Provider
6 | Storage Network Micro Segmentation | Micro segmentation needs to be enabled on Storage Network and Tenant VM´s
7 | VLAN for vMotion | can we use the existing VLANS for vMotion also for the new ESXi Servers
8 | PowerFlex Management ESXi Server | can we include the PF ESXi Servers into our Manangement Vcenter | Best Practise of dell ?
9 | Distribution of ESXi Servers | According to the actual Values, the 25 Prod Servers needs to be distributet to the proper Clusters
10 | Co-existence of old and new Clusters (EVC Mode) | Both old and new ESX Clusters needs to be on an equal or compartible EVC Mode to ensure seamless migration | Best Practise of dell ?
11 | one Vcenter | it is expected that there is no new Prod Vcenter in DNPC
12 | Cabling | There were lots of FC Cables (~180) Pcs.)in the delivery. Does these Calbles fit for the whole Installation, or do Dell expect from DN to apply more Cables between Compute Nodes and ACI ?
13 | Digital SW and License Delivery | How to handle the Software and License Delivery?
14 | Rackspace in the Datacenters | Does the planned Rackspace from DN fits with the Dell Requirements
15 | Power Plugs in Racks | does the available number of Power Plugs fits with the Requirements
16 | Concept for DR Replication | Steel Class Storages need to replicate to the respective other Site
17 | Backup Concept | What needs to Plan for the Backup Solution
18 | Dell Personell Onsite/Remote | During the Solution Implementation, are there and Dell Personel onsite or Online to discuss issus with us?

## Prerequisites
S.No | Servers
1 |  | Type | CPU | RAM | Space for OS | NIC Count | Connectivity Type1 | Connectivity Type2 | Connectivity Type3 | Connectivity Type4 | Quantity
| Physical | Worker nodes | 2 socket 10 core each | 128 GB | 100 GB | 6-8 nics | Management Bond | VM Traffic | Container Node NW | SAN Connection | 3
| Virtual/Physical(in case of Prod ready infra) | Master nodes | 8 vCPUs | 32 GB | 100 GB | 2 nics | Management Bond | NA | NA | NA | 3
| Virtual/Physical(in case of Prod ready infra) | Infrastructure nodes | 8 vCPUs | 32 GB | 100 GB | 2 nics | Management Bond | NA | NA | NA | 3
| Virtual | Bootstrap(temporary) | 8 vCPUs | 32 GB | 100 GB | 2 nics | Management Bond | NA | NA | NA | 1
| Virtual | Jump/Bastion | 8 vCPUs | 32 GB | 100 GB | 2 nics | Management Bond | NA | NA | NA | 1
2 | VLAN/Bond Type | Purpose |  | VLAN | Network | Remarks
| Management VLAN | To build OCP cluster |  | 302 | 100.65.242.0/24 | Network not empty!
| Worker node VLAN(optional) | To add additional workerload Network for containers |  | 302 | 100.65.242.0/24 | Network not empty!
| VM Traffic VLAN | To add VLANs for VM traffic |  | ACI | ACI
| SAN VLAN | To add VLAN for SAN traffic |  | 303 | 100.65.243.0/24 | Network not empty!
3 | IP on Bond Type | Purpose
| Management Ip | To build OCP cluster. One for each node and one additional IP for bootstrap IP. |  | 302 | 100.65.242.0/24 | Network not empty!
| Worker node VLAN | To add additional workerload Network for containers. One for each node |  | 302 | 100.65.242.0/24 | Network not empty!
| VM Traffic VLAN | To add VLANs for VM traffic. One for each node |  | ACI | ACI
| SAN VLAN | To add VLAN for SAN traffic. One for each node |  | 303 | 100.65.243.0/24 | Network not empty!
4 | F5 LB request to get the IPs for OCP API and API-Int connectivity
| URL Users will use to access the service | Protocol/Port for users | Front END IP | Member Server IP address | Protocol/Port Server listens on | SSL Offloading (If yes please attach certificate) | Monitoring (Default TCP port status) | Load Balancing Method (Default Round Robin) | Remarks
| api.dnpcpoc.test-dnpcloud.dieboldnixdorf.com api-int.dnpcpoc.test-dnpcloud.dieboldnixdorf.com | 6443, 22623 |  |  | 6443, 22623 | N/A | Default | Round Robin | Passthrough(layer 4 routing)
| *.apps.dnpcpoc.test-dnpcloud.dieboldnixdorf.com | 443 |  |  | 443 | N/A | Default | Round Robin | SSL
5 | DNS Records
| Cluster | Reqired for | Node/LB | Record (Reversed) | Record Type | IP | MAC | MAC + 1
| Clustername | Load Balancer | api.clutsername.dieboldnixdorf.com | api.dnpcpoc.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.236
|  |  | api-int.clustername.dieboldnixdorf.com | api-int.dnpcpoc.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.236
|  |  | *.apps.clustername.dieboldnixdorf.com | *.apps.dnpcpoc.test-dnpcloud.dieboldnixdorf.com | A | 100.65.242.235
|  | Nodes | bootstrap fqdn | de04mgtlist016.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.99
|  |  | Jump/Bastion/Helper | de03mgtlist015.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.234 | 00:50:56:98:bc:37
|  |  | de04ocp-master1t | de04mgtlapt031.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.101 | 00:50:56:98:c1:1a
|  |  | de04ocp-master2t | de04mgtlapt032.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.102 | 00:50:56:98:bb:e5
|  |  | de04ocp-master3t | de04mgtlapt033.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.103 | 00:50:56:98:2a:31
|  |  | de04ocp-infra1t | de04mgtlapt034.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.104 | 00:50:56:98:21:9e
|  |  | de04ocp-infra2t | de04mgtlapt035.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.105 | 00:50:56:98:67:15
|  |  | de04ocp-infra3t | de04mgtlapt036.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.106 | 00:50:56:98:85:05
|  |  | de04ocp-worker1t | de04fnd010ise31.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.107 | 00:3a:7d:71:5c:ae | af
|  |  | de04ocp-worker2t | de04fnd010ise32.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.108 | 00:78:88:a3:49:e4 | e5
|  |  | de04ocp-worker3t | de04fnd010ise33.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.242.109 | 00:42:68:6f:83:dc | dd
6 | HW Management | Nodes |  | de04fnd010ise31-cimc.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.241.107
|  |  |  | de04fnd010ise32-cimc.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.241.108
|  |  |  | de04fnd010ise33-cimc.test-dnpcloud.dieboldnixdorf.com | A + PTR | 100.65.241.109
6 | Firewall rules
OCP Related
| Purpose | Source | Destination | Port | Protocol
| DNS | OCP Management subnet | Domain controllers | 53 | TCP and UDP
| NTP | OCP Management subnet | Domain controllers | 123 | UDP
| OCP to VIP1 | OCP Management subnet | VIP1 | 6443 22623 | TCP
| OCP to VIP2 | OCP Management subnet | VIP2 | 443 | TCP
| VIP2 to OCP | VIP2 | OCP Management subnet | 443 | TCP
| VIP1 to OCP | VIP1 | OCP Management subnet | 6443 22623 | TCP
| End user access to OCP | AD Security group | OCP Management subnet | 226443 | TCP
| End user access to OCP cluster API | AD Security group | VIP2 | 443 | TCP
| End user access to OCP cluster API internal | AD Security group | VIP1 | 6443 | TCP
| OCP to proxy | 10.52.85.0/24 | Proxy | 8080 | TCP
OpenID related
| Purpose | Source | Destination | Port | Protocol | Direction
| Azure AD authentication (OAuth2) | OpenShift API Server / OAuth Pod | login.microsoftonline.com | 443 | TCP | Outbound
| User info and group membership queries | OpenShift API Server / OAuth Pod | graph.microsoft.com | 443 | TCP | Outbound
| Azure AD UI assets (optional) | OpenShift API Server / OAuth Pod | aadcdn.msftauth.net | 443 | TCP | Outbound
| DNS resolution for | OpenShift API Server / OAuth Pod | DNS servers | 53 | TCP/UDP | Outbound
SAN Related
| purpose | Source | Destination | port | protocol
| Master node to SAN | Master node IPs | SAN IPs | 443 | TCP and UDP
| worker node to SAN | Worker node IPs | SAN IPs | 443 | TCP and UDP
| Infra node to SAN | Infra node IPs | SAN IPs | 443 | TCP and UDP

## LL Tasks
Task # | Type | Task | Start Date | End Date | Status | Task Desc | Expected result | Accountable Lead | Team | Effort (Days) | Comments | Dependencies
1 | Infrastructure | Prepare Hardware for POC in DNPC Test | 24.10.2025 | 27.10.2025 | Complete | remove all old Content and Settings of DNPC Test Vmware to have a clean Environment for RHOS Installation | Hardware is ready for Installation | Juergen |  | 1
2 | Documentation | Create Network and Communication Plan for Initial Installation | 2025-10-16 | 2025-10-17 | Complete | A Network Plan has to be created which conains Networks, Communication requirements, Directions, Port Numbers (VLANs) etc. | ACI Network can be defined from this basic Plan | Krishna |  | 1
3 | Documentation | Fill out the Network Sheet | 2025-10-22 | 2025-11-03 | Complete | Existing Networks are already assigned to the Physical NICS. Assign proper Network Addresses requested in the Network Sheet. Add also DNS Entries to the DNS Server of DNPC Test | All IP Adresses and DNS Entries are defined and configured | Krishna | Adrian | 1
4 | Implementation | Test Hardware Compatibility | 2025-10-27 | 2025-10-28 | Complete | Hardware needs to be checked if it can be used for POC | Hardware is ready for Installation | Juergen | RedHat | 2 | https://access.redhat.com/downloads/content/290/ver=4.20/rhel---9/4.20.0/x86_64/product-software
3 | Documentation | Draw Architecture Picture |  | 2025-11-25 | Complete | A HLD Architecture Picture is needed for the POC | HLD Architecture Picture xists | Krishna | juergen
5 | Implementation | Create Management Client Networks | 2025-11-12 | 2025-11-27 | Complete | the Management Client Network needs to be created | Managemnet Networks are defined in the POC | Juergen | Redhat |  | Blocked by Storage Data Client Implementation
5 | Implementation | Request ACI Network Creation | 2025-11-18 | 2025-11-19 | Complete | Based on the Communication Plan, the ACI Network needs to be created | ACI Network is defined on the APIC | Juergen | viktor |  | Network Controller issue solved
6 | Implementation | Request Firewall Rules | 2025-10-29 | 2025-11-19 | Complete | Based on the Communication Plan, the FW Rules needs to be requested | FW Rules are active for the EPG´s | Jan |  |  | AG-Group needs to be renamed - SMAX 143054847
8 | Infrastructure | Prepare Virtual Hardware for Inital Control Planes and Rollout Environment | 2025-11-03 | 2025-11-03 | Complete | Based on DNPC Vmware Platform, the virtual Hardware for RHOS has to be created including Networks, Storage etc.. | Virtual Hardware is ready for RHOS Installation | Adrian
9 | External Support | OpenShift Cluster Installation | 2025-11-07 | 2025-11-07 | Complete | RedHat will guide/Follow the Basic Installation of the POC | Basic Installation of POC is done | Juergen | RedHat/Team |  | Installation was planned for 04.11.2025 - moved to later due Internet Major Incident
10 | External Support | ACI Intergration to Redhat OpenShift | 2025-11-24 |  | Blocked | ACI is basically supporting RedHat openshift. A documentation and the Implementation has to be created | APIC is connected to RHOS | Viktor |  |  | Blocked: apic upgrade needs to be done
11 | External Support | Dell Storage Connection to RHOS | 2025-11-11 | 2025-11-25 | Complete | The PowerFlex Storage System needs to be integrated into RHOS using the Dell CSI Driver System | the RHOS Installation is consuming Storage from the PowerFlex System | juergen | Dell/RedHat |  | Storage Architecture Discussion ongoing
12 | Infrastructure | NetApp Storage Connection to RHOS |  |  | Complete | NetApp Systems needs to be integrated into RHOS using the NetApp Trident Driver System | the RHOS Installation is consuming Storage from the NetApp System | Naresh | Narender |  | out of Scope for DNPC POC (No NetApp Systems anymore in DNPC)
13 | Procurement | Virtual Migration Assessment (VMA) | 2025-11-11 | 2025-11-18 | Complete | The Virtual Migration Assessment (VMA) needs to be ordered from RedHat | RedHat helps us with HLD and Migration Plan | Juergen |  |  | Ordered. Purchase Order 4100571190
14 | Infrastructure | Firewall Rules for DNPC Test Jumpserver | 2025-10-28 | 2025-11-19 | Complete | a Set of FW Rules needs to be defined and implemented between Jumpserver and RedHat Openshift Consoles | a fresh Installation can be run from the Jumpserver | Jan |  | 2
15 | Infrastructure | New AG Group for POC to access DNPC test | 15.10.2025 | 2025-10-20 | Complete | Creation of Group AG-DN-ADM-DNPC-PCI-ENGINEERING | Engineering Team can access the Jumpserver | Juergen |  | 2
16 | Internal Prep | Accounts for the Team Members needs to be created on the TEST-DNPCLOUD Domain | 2025-11-19 | 2025-11-19 | Complete | A Domain Account for DNPC Test needs to be created, if not already there | Team Members are able to join the DNPC Test environment | Juergen
17 | Implementation | DNPC Test Jumpserver | 15.10.2025 | 2025-10-22 | Complete | Create a new Jumpserver in DNPC Test MGMT for POC activities | A Dedicated Jumpserver is availabe in DNPC Test MGMT | Michal |  | 2
17 | POC Testing | SFTP Private Repo | 2026-02-08 | 2026-02-10 | Complete | For the Container Installation of the SDC Driver the CSI Driver needs SFTP Access to mft.dell.com. This Task is for Discussion/Installation of a Private SFTP Repo instead of having direct Internet Access (FW Rule) | SDC Container is using a Private Repo | Naresh
19 | POC Testing | Integrate vSphere infra to RHOS | 2026-01-12 | 2026-01-16 |  | Need to integrate vSphere infra to RHOS | By doing this we shall have visibility of Vsphere infra from RHOS perspective | Adrian | Krishna
20 | POC Testing | Prepare/build VMs for test migrations - ACI | 01.12.2025 |  | Blocked | Need to build or prepeare VMs in integrated Vsphere infra | These VMs will be used for test migrations | Adrian/Naresh
21 | POC Testing | Prepare/build VMs for test migrations - classic | 2026-02-09 | 2026-02-13 | YTS | We need to find VM in the exisitng VMware Infrastructure which are right candidates to test the migration | Implement migration plan and test the migration. VM should run as is once migrated to OpenShift | Krishna/Naresh
22 | POC Testing | Build test cases to match what we do today in vSphere | 2026-02-09 | 2026-02-26 | WIP | Build test cases to match what we do today in vSphere | These test cases will help to understand how can we improve once moved to RHOS | Adrian |  | 9 | Virtualization tasks'!A1
23 | POC Testing | Build test cases prove containerization service functionalities | 2026-02-06 | 2026-02-13 | WIP | Identify the cases which need to be proved in POC | We need to prove the test cases and provide related artifects | Krishna
24 | POC Testing | License for POC | 2026-02-06 | 2025-02-11 | WIP | Trial License has been expired, but POC is not finished | New Subscription will be installed/Trial extendet | Juergen
25 | POC Testing | Network communication for VMs - ACI |  |  | Blocked | We need to make sure the VMs traffic is running over dedicated bond on Openshift | We need to make sure the VMs are migrated over dedicated bond on Openshift and once the VM is migrated it should run as is. | Adrian
26 | POC Testing | Network communication for VMs - classic | 2026-02-06 | 2026-02-13 | WIP | We need to make sure the VMs traffic is running over dedicated bond on Openshift | We need to make sure the VMs are migrated over dedicated bond on Openshift and once the VM is migrated it should run as is. | Krishna
27 | POC Testing | Network communication for contaners - classic | 2026-02-06 | 2026-02-13 | WIP | We need to make sure the POD communication is running over dedicated bond on Openshift |  | Krishna
28 | POC Testing | Network communication for contaners - ACI |  |  | Blocked |  |  | Adrian
29 | POC Testing | DR test - Classic/Netapp | 2026-02-10 | 2026-02-12 | Complete |  |  | Naresh
30 | POC Testing | DR test - ACI/Powerflex | 2026-02-09 | 2026-02-14 | Blocked | Build up a new Cluster in DC3 to test DR Functionality | a very tiny Cluster in DC3 is available | Juergen
31 | POC Testing | Check Apliance VMs compatibility with openshift | 2026-02-08 | 2026-02-13 | WIP | PFM K8/Clodu Link/UCSD/algosec/ cBox/ LB/ FW etc support under openshift |  | Adrian/Naresh |  |  | DELL SR: 222335620 PFM and CloudLink is supported and homologated
32 | POC | Installation OCP cluster using Assisted Installation | 2026-02-09 | 2026-02-10 | WIP | Install OCP cluster without the need for F5 load balancer for API connectivity | Elemenating the need of external loadbalancer for management connectivity | Krishna/Naresh |  |  | We were able to install the OCP cluster without F5 VIP. Will gather the artifects.
33 | Security | Antivirus Integration with Containers | 2026-02-09 | 2026-02-13 | Blocked | Need to make sure all pods deployed are being scanned by Antivirus and container images are being scanned before getting used | Need to make sure all pods deployed are being scanned by Antivirus and container images are being scanned before getting used | Krishna |  |  | Please find the update from Antivirus team(Jason Potts) on CrowdStrike Container and Container images Scanning:The only ETA we have is 2026. We will not move forward until we are ready and confident.
| POC Testing | Backup - PPDM and openshift | 2026-02-12 | 2026-02-20 | YTS | POC Backup - PPDM and openshift compatibility Context: Standardize backup tool for openshift technology Scope: PPDM and Dell powerflex, excluded netapp Steps: - install PPDM - configure PPDM - storage unit (DDVE mgt in test) - install PPDM to openshift - test backup and restore | VM and containers backup/restore test is documented | Miroslav | Naresh
| POC Testing | Backup - netapp trident protect and openshift | 2026-02-11 | 2026-02-13 | WIP | POC Backup - Netapp TP and openshift compatibility Context: Standardize backup tool for openshift technology Scope: netapp TP and netapp ontap filer, excluded Powerflex storage Steps: - install TP to openshift - configure TP - secrets/application etc | VM and containers backup/restore test is documented | Naresh

## Open Support
Ticket number | Raised Date | Status | Raised by | Escalated | Responsiblity | Problem | Task Impacted | Impact | Ticket Result
[10 empty] | Status | Responsibility
[10 empty] | OPEN | DELL
[10 empty] | CLOSED | DN
[10 empty] | SOLVED | NOT DEFINED
[10 empty] | BLOCKED | DELL & DN

## Input
Type | Status
Clean up | Blocked
DELL Workshop | Complete
Documentation | N/A
External Support | WIP
Finance | YTS
Finance Operations
HR
Implementation
Infrastructure
Internal Prep
Logistics
POC
POC Testing
Process Change
Procurement
Quality Gate
Security
SOW Quality Gate
Testing
Title
Travel

## Pre-Migration testing (hidden)
service | change model | workflows/tasks to be modfied and tested with dell | resp | Status in test | Migration of WF to INT | Status in prod
VM | MS EMEA - DNPC - Jump - Additional jump host with MFA for DN associates - non-privileged access | test wf | Michal | Not relevant, currently transition to DN Associates 2.0 concept - automation does not work | Not relevant, currently transition to DN Associates 2.0 concept - automation does not work | Not relevant, currently transition to DN Associates 2.0 concept - automation does not work
VM | MS EMEA - DNPC - Jump - Customer jump host configuration with MFA | test wf | Marek B | done | done | done
Network | MS EMEA - DNPC - Network - DNPC Application (VIP) deployment on the existing external Loadbalancer | xml script update | Marek H | OK for Dell compute | N/A | Peding LB migration in Prod
Network | MS EMEA - DNPC - Network - DNPC Application (VIP) deployment on the existing internal Loadbalancer | xml script update | Marek H | OK for Dell compute | N/A | Peding LB migration in Prod
Network | MS EMEA - DNPC - Network - DNPC Create EPG for virtual workload | xml script update | Marek H | OK for Cisco and Dell compute | N/A | OK for Cisco and Dell compute
Network | MS EMEA - DNPC - Network - External Loadbalancer and first application (VIP) deployment into a Tenant | xml script update | Marek H | OK for Dell compute | N/A | Peding LB migration in Prod
Network | MS EMEA - DNPC - Network - Internal Loadbalancer and first application (VIP) deployment into a Tenant | xml script update | Marek H | OK for Dell compute | N/A | Peding LB migration in Prod
Network | Add Tenant Oracle DB | xml script update | Marek H | OK for Cisco and Dell compute | N/A | OK for Cisco and Dell compute
| MS EMEA - DNPC - Security - Venafi certificate renewal | test wf | Marek B | OK |  | Done
Storage | MS EMEA - DNPC - Storage - Add Network Attached Storage (NFS or CIFS) | new-storage-NIC (done) netapp-new-nfs(done) netapp-new-cifs (done) tenant storage parition creation (done) | Miroslav | done | done | Done
Tenant | MS EMEA - DNPC - Tenant - Tenant creation | tenant admin jump, vulns scenner WF, deplyment vsec FW - need to test+update docu, test wf new-tenant | Jan, the man | Tenant Admin Jump - deployment OK Vulnerability Scanner - deployment OK vSEC FW deployemt - deployment works, Docu updated New Tenant - testing done, adjustments performed | Done | Done
| MS EMEA - DNPC - VIP - Virtual IP Address Allocation | IP-reserve | Miroslav | done | done | done
| MS EMEA - DNPC - VM - Add RDS Role Service on Application Server | UCSD WF | Michal | done | done | done
VM | MS EMEA - DNPC - VM - Create/Modify/Delete DRS Rule | Create-DRSRule, Set-DRSRule, Delete-DRSRule | Michal | done | done | done
VM | MS EMEA - DNPC - VM - Performance Class Changing | Set-PerformanceClass_v2 | Miroslav | done | done | done
VM | MS EMEA - DNPC - VM - Virtual Disk adding | New-VMwareDisk_v2 | Miroslav | done - adjusted, tested, working |  | will be done in LL task Swap Automation flows
VM | MS EMEA - DNPC - VM - Virtual disk enlarging | Resize-VMvmwareDisk | Miroslav | done | done | done
VM | MS EMEA - DNPC - VM - Virtual Server decommission | vm_delete | Jan, the man | done | done | done
VM | MS EMEA - DNPC - VM - Virtual Server modification (vCPU/vRAM) | Resize_CPU_RAM | Miroslav | done | done | done
VM | MS EMEA - DNPC - VM - Virtual Server provisioning | New-VM New-VM-Common New-VM-MGMT | Michal | New-VM - adjusted, tested, working -Common - adjusted, tested, working -MGMT - adjusdted, testing |  | will be done in LL task Swap Automation flows

## PROD Tenant Migration Framework (hidden)
Tenant Name | Tenant Acronym | Status | Test Available | Production | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
All Transact | ALL | Production | yes | yes |  |  | ALL_IA/TA |  | ALL_PA
BAWAG | BAW | Production | yes | yes |  |  |  | BAW_IA/TA |  | BAW_PA
​​Shared tenant for Benelux customers | ​BNL | Production | yes, Integration | yes |  |  | BNL_IA |  | BNL_PA
​BP Tenant | ​BPT | Production | yes | yes |  |  | BPT_TA |  | BPT_PA
​Configuration Management System | ​CMS | Production | yes | yes |  | CMS_TA |  | CMS_PA
Common | COM | DNPC Production | no | yes | X | [5 empty] | Legend: | X | Tenant has only one Bridge Domain, no segregation between Test and Prod
C&A | CUA | Production | Yes | yes |  |  |  | CUA_TA/DA |  | CUA_PA |  | N/A | Tenant does not have any Virtual Ressources to Migrate, Infrastructure only
Foundation Tenant internal | FND | Infrastructure Tenant only, no Virtual Ressources to Migrate | no | no | N/A | N/A | N/A | N/A | N/A | N/A |  | ALL_XXX, ff. | Name of Bridge Domain in Tenant: TA, DA or IA Indicates Test, Development or Intgegartion, PA indicates Prod
​Hennes And Mauritz | ​HAM | Production | no, SIT only | yes |  |  | HAM_SIT |  | HAM_PA
​Manage Connect Prod | ​MCP | Production | yes | yes |  |  |  |  | MCP_PA
​Manage Connect Test | ​MCT | Test only | yes | no |  | MCT
Radia DE03 | MSA | Production | no | yes |  |  | MSA_PA
DNPC Management | MGTM | Production | no | yes | X
Managed Service Multi Customer Environment DE Prod | MSM | Production | yes | yes |  | MSM_TA |  | MSM_PA/PD
Manage Service Production | MSP | Production | no | yes |  |  | MSP_DZ |  | MSP_PA
Radia DE04 | MSR | Production | yes | yes |  | MSR_TA |  | MSR_PA
Manage Service Test | MST | Test only | yes | no |  |  | MST_TA |  | MST_TI/DZ
Managed Services VynamicView | MSV | Production | yes, Integration | yes |  |  |  | MSV_IA |  | MSV_PA
Oracle | ORA | Infrastructure Tenant only, no Virtual Ressources to Migrate | no | yes | N/A | N/A | N/A | N/A | N/A | N/A
Oracle for Test and Integration Workloads | ORT | Infrastructure Tenant only, no Virtual Ressources to Migrate | yes | no | N/A | N/A | N/A | N/A | N/A | N/A
Proof of Concept | POC | Test Tenant | yes | no | X
​Remote Desktop Services for EMEA | ​RDE | Production | no | yes |  | RDE_PA
​Rossmann | ​ROS | Production | yes | yes |  |  | ROS_TA |  | ROS_PA
​Security Shared Tenant | ​SST | Production | yes | yes |  |  |  | SST_TA/IA |  | SST_PA
Network Tenant internal | TE1 | DNPC Integration | yes | no | N/A
​MS Vynamic transcation engine 1 | ​TM1 | Production | yes | yes |  | TM1_TA |  | TM1_PA
​Transaction Middleware 2 | ​TM2 | Production | no | yes | [5 empty] | TM2_PA
​Transaction Middleware 3 | ​TM3 | Production | yes | yes |  |  | TM3_TA |  | TM3_PA
​Transaction Middleware 4 | ​TM4 | Production | yes | yes |  |  |  | TM4_TA |  | TM4_PA
Network Tenant internal | TN2 | DNPC Integration | yes | no | X
Triumph | TRI | Production | Yes | yes |  | TRI_TA/DA |  | TRI_PA
Total Machines per Phase |  | Total Number of Machines is not accurate, because it is subject of dayli changes! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Estimatet Runtime per Phase |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Virtualization tasks
RedHat OpenShift Virtualization items (with documentation and proof)
| Virtualization task: | Task Description | Expected Result | Start Date | End Date | Priority
1 | Create Project / Namespace | Create namespace | created project OC | 10.2.2026 | 10.2.2026 | Prio 1
2 | Create a VM + all requirements to storage + network | all necessary components for VMs | build VM |  |  | Prio 1
3 | Start, Stop, Restart VM & POD | Operation task | simulate VM and POD restart + monitoring |  |  | Prio 1
4 | Add, Remove, Resize disk | Opration to increase VM performance and LUN |  |  |  | Prio 1
5 | Move disk between VMs
6 | Attach disk / LUN to VM, PV
7 | Moving a Virtual Machine Between Projects / unmount VM
8 | Create, delete VM + related datastores
9 | Increase CPU,RAM, DISK |  |  |  |  | Prio 1
10 | VM Migration from VMware to OpenShift
11 | Importing and cloning existing virtual machines
12 | Disk VM Datastore Labeling
13 | Create Datastore disk (persistent volume)
14 | PersistentVolumeClaims
15 | StorageClasses Gold, Silver, Bronze
16 | IOPS setup StorageClasses & VMs
17 | VM Snapshot – Recovery
18 | Volume snapshots
19 | Templates migration from VMware Win 2016, Win 2019, RHL, OEL
20 | Install VM from template
21 | Modify templates, Patching templates – Lifecycle
22 | Managing Linux and Windows virtual machines (VMs)
23 | Running Guest Agent
24 | Affinity rules
25 | Connecting to virtual machines through a variety of consoles and CLI tools
26 | Managing network interface controllers and storage disks attached to virtual machine
27 | Live migrating virtual machines between nodes
28 | Login to OpenShift / Token
29 | Grant a User Permissions in a Project
30 | Define Access roles
31 | VLAN, EPG definitions in OpenShift
32 | VLAN assignment to VMs
33 | Attach new network card
34 | Define Uplinks
35 | DC Certificate installation to OpenShift
36 | SSO AD Loging OpenID
37 | High availability / Node Remediation
38 | DRS Descheduler Operator
39 | VM Load Balancing
40 | Rack Level Availability
41 | OpenShift Backup and Restore
42 | OpenShift management Tools installation
43 | OC Nodes Maintenance
44 | Checkmk Monitoring
45 | System Log monitoring
46 | Install the Dell NetApp Trident CSM Operator
47 | How to Find VM resources:
48 | Find: IP
49 | Find: VM in Namespace
50 | Find / List VM in All namespaces
51 | List StorageClasses
52 | List all PersistentVolumes:
53 | List all PersistentVolumeClaims (PVCs)
54 | PVCs related to a specific VM:
55 | Relationships (VM → DV → PVC)
56 | Get VM IP address (via VMI)
57 | View all interfaces of a VM |  |  |  |  | Prio 2
58 | Routes |  |  |  |  | Prio 2
59 | Worker Node Location (Which node the VM is running on) |  |  |  |  | Prio 2
60 | Get All VM-Related Resources |  |  |  |  | Prio 2
61 | Network policies |  |  |  |  | Prio 2
62 | cBOX deployment
63 | Migration Toolkit for Virtualization (MTV) |  |  | 8.2.2026 | 9.2.2026

## Containerization POC
S. NO | Task Name | Task Description | Expected Result | Start Date | End Date
1 | Create Namespace/Project | We should be able to create Namespace | The namespace should be visible to Team who have deployed
2 | RBAC on the Namspace | Should be able to apply RBAC | The respective team should have access to respective Namespces only
3 | Pod Network configuration | Pod Network should be configured on dedicated bond | The pod communication should happen over dedicated bond
4 | Network Security policy | Default deny all policy for all pods | Both Ingress and Egress Trafiic should be denied within the namespace and cross namespace
5 | Secrets | Create a secret | We should be able to inject the confidential data into pods
6 | Secondary Network security policy | To allow communication across pods which needed communication | pods which are needed to communicate with on the namespace or other namespace whould talk to each other
7 | Pod Security Admission | Implement SCC so that pod deployment with privilaged access is restricted | The SCCs should not allow pod deployment which requires previlaged access
8 | Replicas | define the number of replicas for anapplication for fault tolerance | The number of replicas should be maintained always. even a pod is deleted a new related pod should created aurtomatically to maintain number of replicas
9 | Horizontal Pod scaling | Increase/decrease the number of pods as per requirement | The number of pods should be above the minimum count when the resource utilization in high and once the utilization is normal oe geting reduced the pod count should be decreasing as per defined monitoring intervel
10 | Vertical Pod scaling | Increase/decrease the pods resources as per requiment | the Pod resource requests and Limits should be changed as per resource utilization
11 | Exposure of Service via Ingress controller | We should be able to expose a service via ingress controller using OCP routes | The service should be able to communicate from other defined networks
12 | TLS Termination for Apps | TLS Termination for Apps | SSL should be terminated on backend servers for end to end encrypted communication
13 | connect second NIC to POD | Using Multus connect second NIC to Pod | Secondary NIC should be added to pod for Network Isolation
14 | Persistence Volume Claims | Add Persistence volume claims to pods | Pods should see the PVCs and able to read/write on it
15 | Data Persistence on pod deletion/restarts | Data Persistence on pod deletion/restarts | Data should be as is even when the pod is deleted/recreated/restarted
16 | Storage class performace | Stouldbe able to test Storage class performance | The output should match the number or IOPs and troughput
17 | Storge traffic via dedicated bond | Storge traffic via dedicated bond | We need to make sure that we are able to get the PVCs on dedicated bond
18 | OCP Floating IP Failover | OCP Floating IP Failover | Once the master node containing the floating IP is down, the floating IP should be assigned to next available master node
19 | Prometheus Metric sraping | Prometheus Metric sraping | Prometheus should scrape the reource utilization details from /metrics
20 | Alerting | Configure Alert Manager | Make sure Alerts are being received once the configured Threshold is reached.
21
22
23