## Planning req for WS (hidden)
Task ID | Task | Task Desc
1 | Sustainable VLAN Scalability | We trunk ~2000 VLANs towards each UCS FI port-channel however with DELL we have to trunk it to all server port-channels or ac-tive/standby links. Each Cisco ACI leaf switch has a certain VLAN scalability (Cisco states 64000). In theory that means a completely unoccupied switch could be used to support only 32 with 2000 VLANs on it (32x2000 = 64000). If this is right (to be confirmed by Cisco) then our existing network infrastructure may not be able to handle the new servers in test and we would also need to validate potential increase in HW investments for Prod. To be Discussed in meeting with Dell Subject Matter Expert. | lldp between Servers and Network
2 | VMM domain configuration on APIC | We use Cisco ACI with VMware VDS Integration where APIC deploys port groups into vCenter. This is achieved by creating Read-Write VMM Domain. The configuration is set with certain policies for config-uring port-channel towards UCS Fis and mac-pinning for vDS itself. We need to ascertain whether we can use the existing domain or whether we have to create a new one for DELL servers (which means new datacenter in vCenter) and for that there are some caveats to en-sure connectivity between the new and existing compute setup to per-form virtual machines vMotion. To be Discussed in meeting with Dell Subject Matter Expert. | new VMM Domain to configure but not necressary to be discussed with Dell
3 | PowerFlex Compute Nodes installed with ESXi Server | what is the Process behind? What can be automatet, what needs to be changed/Add
4 | VLAN for Management | can we use the existing VLANS for Management (1331, 1332,329) also for the new EXSi Servers | Better having new VLAN´s
5 | Networks for in-guest-Storage | Storage Interfaces from VM´s needs to connect to the new Storage Provider
6 | Storage Network Micro Segmentation | Micro segmentation needs to be enabled on Storage Network and Tenant VM´s
7 | VLAN for vMotion | can we use the existing VLANS for vMotion also for the new ESXi Servers
8 | PowerFlex Management ESXi Server | can we include the PF ESXi Servers into our Manangement Vcenter | Best Practise of dell ?
9 | Distribution of ESXi Servers | According to the actual Values, the 25 Prod Servers needs to be distributet to the proper Clusters
10 | Co-existence of old and new Clusters (EVC Mode) | Both old and new ESX Clusters needs to be on an equal or compartible EVC Mode to ensure seamless migration | Best Practise of dell ?
11 | one Vcenter | it is expected that there is no new Prod Vcenter in DNPC
12 | Cabling | There were lots of FC Cables (~180) Pcs.)in the delivery. Does these Calbles fit for the whole Installation, or do Dell expect from DN to apply more Cables between Compute Nodes and ACI ?
13 | Digital SW and License Delivery | How to handle the Software and License Delivery?
14 | Rackspace in the Datacenters | Does the planned Rackspace from DN fits with the Dell Requirements
15 | Power Plugs in Racks | does the available number of Power Plugs fits with the Requirements
16 | Concept for DR Replication | Steel Class Storages need to replicate to the respective other Site
17 | Backup Concept | What needs to Plan for the Backup Solution
18 | Dell Personell Onsite/Remote | During the Solution Implementation, are there and Dell Personel onsite or Online to discuss issus with us?

## LL Tasks
Task # | Type | Task | Start Date | End Date | Status | Task Desc | Expected result | Accountable Lead | Supporting | Team | Effort (Days) | Comments | Dependencies
1 | Internal Prep | gather requrements - Containers | 2025-12-05 | 2025-12-31 | Complete | collect information what are the requerements for Containers service in DN | collected information from all of the stakeholders | Krishna | Adrian, Naresh |  |  | https://dieboldnixdorf.sharepoint.com/:x:/r/teams/ITInfrastructureEngineering/Shared%20Documents/Projects/RedHat%20OpenShift/Data%20Collection/Container_Requirements_Document.xlsx?d=wf31d68cce04f411380a4b0011ae5cc24&csf=1&web=1&e=1xUisp&nav=MTVfe0UwNUE1MzJBLTc0REQtNENBMS1CMzFBLTE5Qjc4RDlGMTU3Qn0
2 | Internal Prep | gather requrements - VMs | 2025-12-05 | 2025-12-19 | Complete | collect information what are the requerements for VMs service in DN | collected information from all of the stakeholders | Krishna | Adrian |  |  | https://dieboldnixdorf.sharepoint.com/:x:/r/teams/ITInfrastructureEngineering/Shared%20Documents/Projects/RedHat%20OpenShift/Data%20Collection/VMs_Requirements_sheet.xlsx?d=w321d4649b3cb4ca1b7ac1a567395b381&csf=1&web=1&e=xNcoxQ
3 | Documentation | design service - Containers service | 2025-12-12 | 2026-02-27 | WIP | This document will provide the the details of service tiers, storage tiers, SLAs, etc along with brief description of services offered under OCP containerization | The Document will be reviewed and should approved before roll out | Krishna | Adrian |  |  | https://dieboldnixdorf.sharepoint.com/:w:/r/teams/ITInfrastructureEngineering/_layouts/15/Doc.aspx?sourcedoc=%7B8C96517F-D61D-46AD-AC96-FCC9B2580C8C%7D&file=RedHat_OpenShift_Container_Platform_Service_Definition.docx&action=default&mobileredirect=true
4 | Documentation | design service - VMs service | 2025-12-12 | 2026-02-25 | WIP | HLD of the service - described all neccessery chapters - installation,operations,license management, backup and recovery, monitring etc.. | service definition approved by stakeholders and service description is created | Adrian | Krishna |  |  | https://dieboldnixdorf.sharepoint.com/:w:/r/teams/ITInfrastructureEngineering/Shared%20Documents/Services/Virtualization/RedHat%20OpenShift%20Virtualization%20definition%20concept.docx?d=w731425ce9f55451c8f9ce04ce92598e0&csf=1&web=1&e=oK69mO
| POC | HW configuratin setup | 2025-12-08 | 2026-01-06 | WIP | cabling, racking etc | document condig standard | Juergen | Viktor |  | 3
| POC | Redhat installation | 2026-01-06 | 2026-01-16 | WIP | redhat/openshift installation, cluster/multi-cluster config, storage etc.. | document config standard | Juergen |  |  | 5
4 | Documentation | Cost Comparison Overview | 2025-12-17 | 2025-12-19 | Complete | Based on the RFP Results, create an Overview of expected RedHat Subscription Costs and Combinations | Management Presentation is created | Juergen | Stuart |  | 3
| Documentation | Networking design for containers(ACI +classic) | 2026-02-15 | 2026-02-27 | YTS | This Defines, what Firewall ports are needed to communicate with OCP cluster and how the traffic for management, containers and storage is defined | This information will be provided to Network team for their approval | Krishna |  |  |  | A link will be provided for containerization config standards
|  | Networking design for VMs(classic) | 2026-02-15 |  |  | to create network design | approved network design by network team + documentation | Adrian
| Implementation | Networking design for VMs (ACI) | 2026-02-15 |  | Blocked | to create network design | approved network design by network team + documentation | Adrian | Viktor
3 | Implementation | config standard Containers services | 2025-12-15 | 2026-02-27 | YTS | This task will define the list of functionalities which are needed to run containerization service. | Every Functionalilty listed will be, provided with needed commands or playbooks to implement the same | Krishna | Adrian |  |  | A link will be provided for containerization config standards
| Implementation | config standard VMs services | 2026-01-07 | 2026-02-26 |  | to create config standard for openshift virtualization
| Implementation | Storage design & implementation | 2026-01-14 | 2026-02-24 | WIP | Context: Providing of storage for VMS and Containers from backend storage Scope: Covers Design and document an optimal StorageClass configuration based on the STAC and STPC requirements, Document the installation and configuration of the CSI/CSM storage plugins. Exclude performance,DR and provision tests Steps: - study options and functionalities of csi trident and csm dell plugins for openshift - document the isntallation of CSI/CSM for netapp and dell powerflex - create required storage classes - document the config | Trident and PowerFlex CSI/CSM installed and Ready. All required StorageClasses created with correct parameters. Docs provided | Miroslav | Juergen, Naresh
5 | Implementation | monitoring service | 2026-01-08 | 2026-01-22 | WIP | define monitoring methods for all components define componentes and values for alert/performance monitring configure and test | Design is proven and test results documented Configuration standard is documented | Adrian | Naresh
5 | Testing | backup and recovery | 2026-01-21 | 2026-02-25 | WIP | Context: All openshift components needs to be backed up. Scope: HW, Manifest, VMs, containers, internal DB, tools netap trident protect and PPDM Steps: - installing of backup tools (netapp trident protect and PPDM) - creating standard policies, configs in backup tools to cover backup of the components - backup and restore test of VM/containr from local snapshot and offloaded backup | Config standard for installation and condifuration of backup components | Naresh | Miroslav
6 | Implementation | DR service | 2026-01-21 | 2026-02-25 | WIP | define DR configuration for all componentes and test the setup context: VM and container services must be albe to perform DR based on STAC scope: operatonal manual for DR of VM and container services in DR datacenter, DR of PVC and also manifest files Steps: - check and prapere moduls for replication (TMR, dell powerflex) - define and document steps for DR scenario | DR configuration is proven and test result documented | Naresh | Miroslav
8 | Implementation | Logging and SIEM Service | 2026-02-15 |  | WIP | Define the Logging and SIEM setings | SIEM Requirements fulfiled | Adrian
9 | Implementation | Hardening Procedures and IS Requirements | 2026-02-15 |  | YTS | Perform a Hardening according to the MSB of OpenShift | preperation for the Vulnerability Scan | Naresh
10 | Implementation | Single Sign on, Right and Roles Concept | 2026-02-15 |  | YTS | Connect the Platform to Directory Services (LDAP/AD/Azure) Define roles and Rights on Directory Groups | no Local Login is necressary for Operation | Adrian
11 | Implementation | Vulnerability Scan | 2026-02-11 | 2026-02-14 | YTS | as a Check of the hardening settings, a vulnerability Scan has to be performed | no critical and high Vulnerabilities present | Juergen |  |  | 5
12 | Implementation | Security as a policy | 2026-02-15 | 2026-02-27 | YTS | This Task will define theNetwork policies and pod security admission policies. In general they will define what communication is allowed between the pods and how the pod should be deployed under a namespace | By default the pod to pod communication will be denied and deployment of pod where pod requires privilaged access is denied | Krishna |  |  |  | A link will be provided for containerization config standards
13
14
15
16
17
17
19
20
21

## Open Support
Ticket number | Raised Date | Status | Raised by | Escalated | Responsiblity | Problem | Task Impacted | Impact | Ticket Result
[10 empty] | Status | Responsibility
[10 empty] | OPEN | DELL
[10 empty] | CLOSED | DN
[10 empty] | SOLVED | NOT DEFINED
[10 empty] | BLOCKED | DELL & DN

## Input
Type | Status
Clean up | Blocked
RedHat Workshop | Complete
Documentation | N/A
External Support | WIP
Finance | YTS
Finance Operations
HR
Implementation
Infrastructure
Internal Prep
Logistics
POC
POC Testing
Process Change
Procurement
Quality Gate
Security
SOW Quality Gate
Testing
Title
Travel

## Pre-Migration testing (hidden)
service | change model | workflows/tasks to be modfied and tested with dell | resp | Status in test | Migration of WF to INT | Status in prod
VM | MS EMEA - DNPC - Jump - Additional jump host with MFA for DN associates - non-privileged access | test wf | Michal | Not relevant, currently transition to DN Associates 2.0 concept - automation does not work | Not relevant, currently transition to DN Associates 2.0 concept - automation does not work | Not relevant, currently transition to DN Associates 2.0 concept - automation does not work
VM | MS EMEA - DNPC - Jump - Customer jump host configuration with MFA | test wf | Marek B | done | done | done
Network | MS EMEA - DNPC - Network - DNPC Application (VIP) deployment on the existing external Loadbalancer | xml script update | Marek H | OK for Dell compute | N/A | Peding LB migration in Prod
Network | MS EMEA - DNPC - Network - DNPC Application (VIP) deployment on the existing internal Loadbalancer | xml script update | Marek H | OK for Dell compute | N/A | Peding LB migration in Prod
Network | MS EMEA - DNPC - Network - DNPC Create EPG for virtual workload | xml script update | Marek H | OK for Cisco and Dell compute | N/A | OK for Cisco and Dell compute
Network | MS EMEA - DNPC - Network - External Loadbalancer and first application (VIP) deployment into a Tenant | xml script update | Marek H | OK for Dell compute | N/A | Peding LB migration in Prod
Network | MS EMEA - DNPC - Network - Internal Loadbalancer and first application (VIP) deployment into a Tenant | xml script update | Marek H | OK for Dell compute | N/A | Peding LB migration in Prod
Network | Add Tenant Oracle DB | xml script update | Marek H | OK for Cisco and Dell compute | N/A | OK for Cisco and Dell compute
| MS EMEA - DNPC - Security - Venafi certificate renewal | test wf | Marek B | OK |  | Done
Storage | MS EMEA - DNPC - Storage - Add Network Attached Storage (NFS or CIFS) | new-storage-NIC (done) netapp-new-nfs(done) netapp-new-cifs (done) tenant storage parition creation (done) | Miroslav | done | done | Done
Tenant | MS EMEA - DNPC - Tenant - Tenant creation | tenant admin jump, vulns scenner WF, deplyment vsec FW - need to test+update docu, test wf new-tenant | Jan, the man | Tenant Admin Jump - deployment OK Vulnerability Scanner - deployment OK vSEC FW deployemt - deployment works, Docu updated New Tenant - testing done, adjustments performed | Done | Done
| MS EMEA - DNPC - VIP - Virtual IP Address Allocation | IP-reserve | Miroslav | done | done | done
| MS EMEA - DNPC - VM - Add RDS Role Service on Application Server | UCSD WF | Michal | done | done | done
VM | MS EMEA - DNPC - VM - Create/Modify/Delete DRS Rule | Create-DRSRule, Set-DRSRule, Delete-DRSRule | Michal | done | done | done
VM | MS EMEA - DNPC - VM - Performance Class Changing | Set-PerformanceClass_v2 | Miroslav | done | done | done
VM | MS EMEA - DNPC - VM - Virtual Disk adding | New-VMwareDisk_v2 | Miroslav | done - adjusted, tested, working |  | will be done in LL task Swap Automation flows
VM | MS EMEA - DNPC - VM - Virtual disk enlarging | Resize-VMvmwareDisk | Miroslav | done | done | done
VM | MS EMEA - DNPC - VM - Virtual Server decommission | vm_delete | Jan, the man | done | done | done
VM | MS EMEA - DNPC - VM - Virtual Server modification (vCPU/vRAM) | Resize_CPU_RAM | Miroslav | done | done | done
VM | MS EMEA - DNPC - VM - Virtual Server provisioning | New-VM New-VM-Common New-VM-MGMT | Michal | New-VM - adjusted, tested, working -Common - adjusted, tested, working -MGMT - adjusdted, testing |  | will be done in LL task Swap Automation flows

## PROD Tenant Migration Framework (hidden)
Tenant Name | Tenant Acronym | Status | Test Available | Production | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
All Transact | ALL | Production | yes | yes |  |  | ALL_IA/TA |  | ALL_PA
BAWAG | BAW | Production | yes | yes |  |  |  | BAW_IA/TA |  | BAW_PA
​​Shared tenant for Benelux customers | ​BNL | Production | yes, Integration | yes |  |  | BNL_IA |  | BNL_PA
​BP Tenant | ​BPT | Production | yes | yes |  |  | BPT_TA |  | BPT_PA
​Configuration Management System | ​CMS | Production | yes | yes |  | CMS_TA |  | CMS_PA
Common | COM | DNPC Production | no | yes | X | [5 empty] | Legend: | X | Tenant has only one Bridge Domain, no segregation between Test and Prod
C&A | CUA | Production | Yes | yes |  |  |  | CUA_TA/DA |  | CUA_PA |  | N/A | Tenant does not have any Virtual Ressources to Migrate, Infrastructure only
Foundation Tenant internal | FND | Infrastructure Tenant only, no Virtual Ressources to Migrate | no | no | N/A | N/A | N/A | N/A | N/A | N/A |  | ALL_XXX, ff. | Name of Bridge Domain in Tenant: TA, DA or IA Indicates Test, Development or Intgegartion, PA indicates Prod
​Hennes And Mauritz | ​HAM | Production | no, SIT only | yes |  |  | HAM_SIT |  | HAM_PA
​Manage Connect Prod | ​MCP | Production | yes | yes |  |  |  |  | MCP_PA
​Manage Connect Test | ​MCT | Test only | yes | no |  | MCT
Radia DE03 | MSA | Production | no | yes |  |  | MSA_PA
DNPC Management | MGTM | Production | no | yes | X
Managed Service Multi Customer Environment DE Prod | MSM | Production | yes | yes |  | MSM_TA |  | MSM_PA/PD
Manage Service Production | MSP | Production | no | yes |  |  | MSP_DZ |  | MSP_PA
Radia DE04 | MSR | Production | yes | yes |  | MSR_TA |  | MSR_PA
Manage Service Test | MST | Test only | yes | no |  |  | MST_TA |  | MST_TI/DZ
Managed Services VynamicView | MSV | Production | yes, Integration | yes |  |  |  | MSV_IA |  | MSV_PA
Oracle | ORA | Infrastructure Tenant only, no Virtual Ressources to Migrate | no | yes | N/A | N/A | N/A | N/A | N/A | N/A
Oracle for Test and Integration Workloads | ORT | Infrastructure Tenant only, no Virtual Ressources to Migrate | yes | no | N/A | N/A | N/A | N/A | N/A | N/A
Proof of Concept | POC | Test Tenant | yes | no | X
​Remote Desktop Services for EMEA | ​RDE | Production | no | yes |  | RDE_PA
​Rossmann | ​ROS | Production | yes | yes |  |  | ROS_TA |  | ROS_PA
​Security Shared Tenant | ​SST | Production | yes | yes |  |  |  | SST_TA/IA |  | SST_PA
Network Tenant internal | TE1 | DNPC Integration | yes | no | N/A
​MS Vynamic transcation engine 1 | ​TM1 | Production | yes | yes |  | TM1_TA |  | TM1_PA
​Transaction Middleware 2 | ​TM2 | Production | no | yes | [5 empty] | TM2_PA
​Transaction Middleware 3 | ​TM3 | Production | yes | yes |  |  | TM3_TA |  | TM3_PA
​Transaction Middleware 4 | ​TM4 | Production | yes | yes |  |  |  | TM4_TA |  | TM4_PA
Network Tenant internal | TN2 | DNPC Integration | yes | no | X
Triumph | TRI | Production | Yes | yes |  | TRI_TA/DA |  | TRI_PA
Total Machines per Phase |  | Total Number of Machines is not accurate, because it is subject of dayli changes! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Estimatet Runtime per Phase |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!